## Sheet1
Fulbright Road Map FY25 - Program Administration and Resources
It is possible to select multiple month filters at the same time - when a filter is active, the X on the top right is red. Click the red X to clear an active filter.
Program | Activity | Responsibility | Resources | Timeline Notes | Start Date | End Date | January | February | March | April | May | June | July | August | September | October | November | December
FLTA | IIE launches the 2025-26 FLTA Application and provides FLTA Application Guide for distribution to potential applicants. | IIE | Fulbright Online Application (Slate) - FLTA 2025-26 |  | 2024-02-01 | 2025-04-01 | January | February | March | April | May | June | July | August | September | October | November | December
FLTA | Commissions and Posts determine recruitment and nomination timeline, make adjustments to Country Specific Information fields on the FLTA 2024-25 Application as needed and review the recruitment cable shared by ECA. | Commission/Post | Foreign Fulbright Online - FLTA 25-26 Launch Template* * Submission of the Launch Template is voluntary and is not required. |  | 2024-02-15 | 2025-03-01 | January | February | March | April | May | June | July | August | September | October | November | December
FLTA | Commissions and Posts transmit dossiers to IIE, ECA, and Fulbright Foreign Scholarship Board (FFSB) for review and approval on or before deadline established in ECA recruitment cable (contact IIE if you need a copy of cable). | Commission/Post | Commission/Post Portal - FLTA Slate Application Resources |  | 2024-09-01 | 2025-02-15 | January | February | [6 empty] | September | October | November | December
FLTA | IIE conducts technical and plagiarism review, follows up with Commissions and Posts for missing documents and clarifications, and troubleshoots submission issues. | IIE | Foreign Fulbright Online – FLTA Placement Resources |  | 2024-10-01 | 2025-03-01 | January | February | March | [6 empty] | October | November | December
FLTA | Commissions and Posts provide responses and documentation in response to IIE technical and material review. | Commission/Post | IIE Partner Portal |  | 2024-10-01 | 2025-03-01 | January | February | March | [6 empty] | October | November | December
FLTA | IIE launches U.S. host institution application, reviews host application submissions, and selects potential recipients. | IIE | Foreign Fulbright Online - U.S. Host Institution Application |  | 2024-10-23 | 2025-02-28 | January | February | [7 empty] | October | November | December
FLTA | IIE begins preparations for the FLTA enrichment opportunities. | IIE | Foreign Fulbright Online – FLTA Orientations |  | 2024-11-01 | 2025-07-15 | January | February | March | April | May | June | July |  |  |  | November | December
FLTA | IIE conducts training for placement process, sends invitations to candidates and host institutions to access Applicant Institution Matching System (AIMS) for ranking, and analyzes review submissions. IIE begins making tentative FLTA and host institution matches. | IIE | Webinar: Matching Process Overview for FLTA Candidates |  | 2025-03-01 | 2025-04-30 |  |  | March | April
FLTA | Commissions and Posts submit required documents for DS-2019 form, which include signed terms, passport, medical form, and signed orientation terms. | Commission/Post | IIE Partner Portal |  | 2025-03-01 | 2025-06-30 |  |  | March | April | May | June
FLTA | FLTA host institution and U.S. Summer Orientation placements are confirmed, and notifications are sent to Commissions and Posts via email. Terms are uploaded to the Partner Portal for Commissions and Posts to send to selected candidates. | IIE | IIE Partner Portal |  | 2025-04-01 | 2025-06-30 |  |  |  | April | May | June
FLTA | IIE monitors document submission and issues DS- 2019s for confirmed participants. IIE completes preparations for FLTA arrivals, including booking travel for Post participants and sharing arrival instructions with participants. | IIE | Foreign Fulbright Online - Guidelines for Issuing a DS-2019 Form |  | 2025-04-01 | 2025-07-31 |  |  |  | April | May | June | July
FLTA | Commissions and Posts assist confirmed FLTAs with visa applications and Commissions book travel as needed. | Commission/Post | Foreign Fulbright Online – FLTA Arrival Instructions |  | 2025-04-15 | 2025-07-31 |  |  |  | April | May | June | July
FLTA | FLTAs attend the FLTA Arabic Pre-Departure Orientation and FLTA U.S. Summer Orientations. * FLTA Arabic PDO and Orientations are planned to be virtual for Summer 2024 | Grantee | Foreign Fulbright Online – FLTA Orientations |  | 2025-07-01 | 2025-08-30 | [6 empty] | July | August
FLTA | IIE collects arrival details and required documentation from participants for validation and holds webinars for late arrivals. IIE ensures successful adjustment and actively reaches out to FLTAs and host institutions. | IIE | Foreign Fulbright Online – FLTA Arrival Steps |  | 2025-08-01 | 2025-09-30 | [7 empty] | August | September
FLTA | IIE informs program partners of FLTAs’ achievements and of any challenges as FLTAs adjust and participate in their programs. | IIE |  |  | 2025-08-01 | 2026-06-30 | January | February | March | April | May | June |  | August | September | October | November | December
Foreign Student - Candidates | Commissions & Posts launch their country competitions in Slate by country/award. | Commission/Post | Fulbright Online Application Management System (Slate) | Commission/Post timelines vary by country and must provide sufficient time for application and selection processes based on placement type. | 2025-01-15 | 2025-05-15 | January | February | March | April | May
Foreign Student - Candidates | Commissions & Posts transmit IIE-Placed dossiers to IIE, ECA, and Fulbright Foreign Scholarship Board (FFSB) for review and approval on or before October 1 deadline with a priority deadline of September 15. | Commission/Post | Fulbright Online - Commissions and Posts/Application Management Resources |  | 2024-09-01 | 2024-10-01 | [8 empty] | September | October
Foreign Student - Candidates | IIE conducts technical, plagiarism, and placement reviews, finalizes submission plans, submits applications, pursues financial aid, and makes Long-Term English recommendations for IIE-placed panels. | IIE | Foreign Fulbright Online - Commissions and Posts/Placement Resources |  | 2024-09-01 | 2025-02-28 | January | February | [6 empty] | September | October | November | December
Foreign Student - Candidates | Commissions, Posts, & ECA provide feedback and approval to IIE on candidates, submission plans, awards, and university admissions for candidates. | Commission/Post | IIE Partner Portal |  | 2024-10-01 | 2025-02-28 | January | February | [7 empty] | October | November | December
Foreign Student - Candidates | IIE launches the global Fulbright online application for the next cycle and sends test preparation materials to Commissions & Posts. | IIE | Fulbright Online Application Management System (Slate) |  | 2025-01-01 | 2025-05-30 | January | February | March | April | May
Foreign Student - Candidates | IIE receives Self-Placed Panels, which are due on or before March 1. IIE conducts follow-up for missing items and records FFSB approvals. | IIE | Foreign Fulbright Online - Commissions and Posts/Guidelines for Issuing a DS-2019 Form |  | 2025-01-01 | 2025-04-01 | January | February | March | April
Foreign Student - Candidates | IIE finalizes placements and university and IIE-endowed support and presents estimated budgets to ECA & Commissions. | IIE | IIE Partner Portal |  | 2025-01-15 | 2025-05-31 | January | February | March | April | May
Foreign Student - Candidates | Pre-Academic/Gateway invitations and assignments are made. Participation is confirmed via signed terms in the Partner Portal. | IIE | Foreign Fulbright Online - Commissions and Posts/ Pre-Academic Information |  | 2025-04-15 | 2025-07-15 |  |  |  | April | May | June | July
Foreign Student - Candidates | Commissions & Posts submit required documents for initial DS-2019 form, which include signed terms, J-1 and financial verifications, passport, and medical form. | Commission/Post | Foreign Fulbright Online - Commissions and Posts/ Guidelines for Issuing a DS-2019 Form |  | 2025-02-15 | 2025-07-31 |  | February | March | April | May | June | July
Foreign Student - Candidates | IIE produces initial DS-2019s for Pre-Academic students and begins production of DS-2019s for summer/fall arrivals. | IIE | Foreign Fulbright Online - Commissions and Posts/ Guidelines for Issuing a DS-2019 Form |  | 2025-04-15 | 2025-08-15 |  |  |  | April | May | June | July | August
Foreign Student - Candidates | IIE monitors summer programming and conducts site visits for Pre-Academic sites and holds Gateway Orientation. | IIE | Foreign Fulbright Online - Commissions and Posts/ Pre-Academic Information |  | 2025-06-01 | 2025-09-30 | [5 empty] | June | July | August | September
Foreign Student - Candidates | IIE collects arrival details and required documentation from new participants for validations and holds arrival webinars. IIE ensures successful adjustment and actively reaches out to on-campus support (Academic Advisors, International Student Advisors) | Grantee | Foreign Fulbright Online - Current Fulbrighters/ Arrival |  | 2025-06-01 | 2025-09-30 | [5 empty] | June | July | August | September
Foreign Student - Candidates | IIE completes preparations for student arrivals, including the issuance of grant documents, DS-2019s, and first stipend payments. | IIE | Fulbright Online - Commissions and Posts/ Program Resources. Fulbright Online - Current Fulbrighters/ Before You Arrive / Pre-Departure Orientation |  | 2025-08-01 | 2025-09-30 | [7 empty] | August | September
Foreign Student - Current Grantees | IIE engages in student advising and monitoring for all active cohorts, which includes J-1 visa compliance, ensuring timely payments, emergency management, campus visits, administering surveys, sending email updates and reminders, and requesting reports from participants. | Grantee | Fulbright Online - Current Fulbrighters | Year-Round | 2024-09-01 | 2025-09-01 | January | February | March | April | May | June | July | August | September | October | November | December
Foreign Student - Current Grantees | IIE’s fall (August-December) tuition fiscal management. | Grantee |  |  | 2024-08-01 | 2024-12-31 | [7 empty] | August | September | October | November | December
Foreign Student - Current Grantees | Invitations are sent and preparations made for Fulbright enrichment seminars. | IIE | Fulbright Online - Current Fulbrighters / Enrichment Seminars |  | 2024-11-15 | 2024-12-15 | [10 empty] | November | December
Foreign Student - Current Grantees | Virtual enrichment opportunities offered to all active cohorts | IIE | Fulbright Online - Current Fulbrighters / Virtual Enrichment |  | 2024-10-01 | 2025-04-30 | January | February | March | April | [5 empty] | October | November | December
Foreign Student - Current Grantees | IIE requests that participants provide non-US tax IDs via the Participant Portal and provides resources to apply for US tax IDs. | IIE | Fulbright Online – Current Fulbrighters / Reporting Your Taxes |  | 2024-09-01 | 2024-11-01 | [8 empty] | September | October | November
Foreign Student - Current Grantees | IIE assesses participant progress, holds renewal/extension interviews and/or office hours, seeks sponsor approval on renewal funding, and issues grant renewals/extensions of visa sponsorship. | Grantee | Fulbright Online - Current Fulbrighters. Fulbright Online - Current Fulbrighters/ Maintain Your Status |  | 2024-12-01 | 2025-07-01 | January | February | March | April | May | June | July |  |  |  |  | December
Foreign Student - Current Grantees | IIE’s winter (January – February) tuition fiscal management. | Grantee |  |  | 2025-01-01 | 2025-02-28 | January | February
Foreign Student - Current Grantees | IIE continues student monitoring and campus visits, including Long-Term English arrivals. Visting Student Researcher (VSR) Virtual Community Day takes place. | IIE | Fulbright Online - Current Fulbrighters/ Before You Arrive / Pre-Academic Programs |  | 2025-01-01 | 2025-02-28 | January | February
Foreign Student - Current Grantees | Commissions, Posts, & ECA provide feedback/approval to IIE on award renewals/extensions, as applicable. | Commission/Post |  |  | 2025-02-01 | 2025-05-15 |  | February | March | April | May
Foreign Student - Current Grantees | IIE communicates tax responsibilities to participants, in collaboration with Sprintax, providing a webinar and other support resources to complete their return and digitally delivers IIE-administered participant 2022 IIE tax form by the IRS deadline of March 15. | IIE | Fulbright Online – Current Fulbrighters / Reporting Your Taxes |  | 2025-02-01 | 2025-04-15 |  | February | March | April
Foreign Student - Current Grantees | IIE processes departure documentation and coordinates travel for incoming and departing Post participants. | IIE | Fulbright Online - Current Fulbrighters/ Completing Your Program |  | 2025-02-15 | 2025-09-30 |  | February | March | April | May | June | July | August | September
Foreign Student - Current Grantees | IIE’s spring/summer (May-August) tuition fiscal management. | Grantee |  |  | 2025-05-01 | 2025-08-31 |  |  |  |  | May | June | July | August
Foreign Student - Current Grantees | IIE uploads Certificates of Completion to the Participant Portal for grant completions on a quarterly basis (November 1, February 1, May 1, and August 1) | IIE |  |  | 2024-11-01 | 2025-08-01 | January | February | March | April | May | June | July | August |  |  | November | December
Foreign Student - Current Grantees | IIE administers alumni survey to participants who completed their grant approximately one year ago. | Grantee |  |  | 2025-06-01 | 2025-08-31 | [5 empty] | June | July | August
Foreign Student - Current Grantees | IIE administers baseline and final surveys to participants on a rolling basis based on grant start and end date. | Grantee |  |  | 2024-09-01 | 2025-09-01 | January | February | March | April | May | June | July | August | September | October | November | December
U.S. Scholar | 2024-2025 Participants arrive in host country depending on country openings (in addition to previous year cohorts who may still be on program). *Participants are expected to begin their program by June 1, 2025 | Grantee | Scholar Website - U.S. Scholar Grantee Resources Page | Start dates vary, but grants should begin no later than June 1, 2025 | 2024-07-01 | 2025-05-30 | January | February | March | April | May |  | July | August | September | October | November | December
U.S. Scholar | 2025-2026 Application Deadline: September 16, 2024* *Varying deadlines for IEA programs | IIE | Fulbright Scholar Website - U.S. Scholar Awards/Application Steps |  | 2024-09-16 | 2024-09-16 | [8 empty] | September
U.S. Scholar | IIE conducts Preliminary Eligibility Review | IIE | Scholar Website - Award Search; Fulbright Online Application Management System (Slate) |  | 2024-09-15 | 2024-09-30 | [8 empty] | September
U.S. Scholar | Discipline-based Peer Review committee meetings takes place virtually | IIE |  |  | 2024-10-16 | 2024-11-19 | [9 empty] | October | November
U.S. Scholar | IIE transmits recommended candidates to Commissions and Posts via the FFSB Transmittal System | IIE | FFSB Transmittal System |  | 2024-11-21 | 2024-12-20 | [10 empty] | November | December
U.S. Scholar | IIE notifies applicants of the outcome of peer review meetings | IIE |  |  | 2024-12-01 | 2024-12-31 | [11 empty] | December
U.S. Scholar | Commissions and Posts edit and review the 2025-2026 Catalog of Awards | Commission/Post | Scholar Website - Commission & Post Resources Password: Resources |  | 2024-11-15 | 2024-12-13 | [10 empty] | November | December
U.S. Scholar | Commission/Post make U.S. Scholar selections in Slate | Commission/Post | Fulbright Online Application Management System (Slate |  | 2024-12-01 | 2025-02-15 | January | February | [9 empty] | December
U.S. Scholar | IIE sends select/non-select/alternate letters once ECA reviews and FFSB approve selections | IIE |  | Ongoing for alternate upgrades | 2025-01-01 | 2025-04-15 | January | February | March | April
U.S. Scholar | Catalog of Awards and online application in Slate launches for 2025-2026 | IIE | Scholar Website - Award Search |  | 2025-02-10 | 2025-02-10 |  | February
U.S. Scholar | Commission/Post Update Country Pages for Pre-Departure Resources web pages | Commission/Post | Guidance will be available on https://fulbrightscholars.org/resources/resources-fulbright-commissions-foundations-and-posts. Password = Resources. |  | 2025-02-01 | 2025-02-21 |  | February
U.S. Scholar | IIE sends introductory emails to selectees about next steps and medical clearance directing them to U.S. Scholar Grantee Resources. · IIE confirms grant details, start, length, and number of dependents for participants going to Post countries. | IIE | Scholar Website - U.S. Scholar Grantee Resources Page | Ongoing for alternate upgrades | 2025-03-01 | 2025-06-01 |  |  | March | April | May | June
U.S. Scholar | Selectees submit Medical Forms, Proof of Citizenship, and signed Terms and Conditions. Commissions/Posts access medical reports via Partner Portal | Grantee | Selectees must submit medical form no earlier than six months before departure. IIE Partner Portal | This is the busy period for document collection, but some documents are collected outside of these months depending on start date | 2025-05-01 | 2025-08-30 |  |  |  |  | May | June | July | August
U.S. Scholar | IIE distributes and collects Grant Documents and Program Terms and Conditions through the Participant Portal. Commissions and Posts can access signed Grant Documents and request medical forms via the Partner Portal. IIE reviews and approves travel for participants to Post countries | IIE | IIE Partner Portal | This is the busy period for distributing and collecting grant documents, but these documents may be collected outside of these months depending on start date | 2025-05-01 | 2025-08-30 |  |  |  |  | May | June | July | August
U.S. Scholar | Enroll participants in ASPE | Commission/Post | IIE enrolls participants in Post countries. Commissions enroll their participants. | Timeline can vary depending on grantee start date. | 2025-05-01 | 2025-08-30 |  |  |  |  | May | June | July | August
U.S. Scholar | IIE hosts Pre-Departure Orientations for participants to Post countries | IIE | Scholar Website - Pre-Departure Orientations |  | 2025-06-01 | 2025-07-30 | [5 empty] | June | July
U.S. Scholar | IIE administers baseline survey to participants before arrival in country | IIE |  | Baseline surveys are distributed ahead of grant start dates | 2025-07-01 | 2026-02-28 | January | February |  |  |  |  | July | August | September | October | November | December
U.S. Scholar | 2025-26 Participants arrive in host country | Grantee | Scholar Website - U.S. Scholar Grantee Resources Page | Start dates vary, but grants should begin no later than June 1, 2026 | 2025-07-01 | 2026-05-30 | January | February | March | April | May |  | July | August | September | October | November | December
U.S. Scholar | IIE administers mid-term monitoring survey to participants who are on grant longer than six months, and after every Flex segment | IIE |  | Varies depending on grant start date | 2025-11-01 | 2026-05-30 | January | February | March | April | May | [5 empty] | November | December
U.S. Scholar | IIE administers final survey to participants upon completion of grant | IIE |  | Varies depending on grant end date | 2025-12-01 | 2026-08-01 | January | February | March | April | May | June | July | August |  |  |  | December
U.S. Scholar | IIE sends certificates upon completion of grant and after final survey has been submitted. Grantees retrieve the certificates from the participant portal. | IIE |  | IIE sends certificates quarterly | 2025-12-01 | 2026-08-01 | January | February | March | April | May | June | July | August |  |  |  | December
U.S. Student | IIE notifies 2025-26 applicants of semi-finalist and non-select status by Jan. 31 | IIE | Information for semi-finalists: U.S. Fulbright Online - Recommended Candidates. · Final Status Notification Timeline. · PDO Dates |  | 2024-12-20 | 2025-01-31 | January | [10 empty] | December
U.S. Student | Semi-finalists’ application review and selections by Commissions/Posts: Dec. 20 – Mar. 31 | Commission/Post | Commission/Post Portal |  | 2024-12-20 | 2025-03-31 | January | February | March | [8 empty] | December
U.S. Student | Resources/Instructions for 2025-26 Application Review provided to Commissions/Posts | Commission/Post | Available on the Resources tab of the Commission/Post Portal. |  | 2025-01-20 | 2025-03-31 | January | February | March
U.S. Student | IIE submits 2025-26 semi-finalist panels via FFSB Transmittal functionality in Slate by Feb. 1 | IIE | FFSB Transmittal System |  | 2025-01-20 | 2025-02-01 | January | February
U.S. Student | Updates to Country Profiles due mid-February for launch of 2026-27 application cycle | Commission/Post | Current country profiles available here for reference: U.S. Fulbright Online – Country Content. Country Content Management System (CCMS) will be shared with Commissions/Posts at end of January/ beginning of February to make updates. |  | 2025-01-30 | 2025-02-16 | January | February
U.S. Student | 2026-27 Application Cycle Opens Late March/Early April 2024 and closes mid-October | IIE | U.S. Fulbright Online - Competition Selection |  | 2025-03-31 | 2025-10-15 |  |  | March | April | May | June | July | August | September | October
U.S. Student | 2025-26 Finalists (Selectees/Alternates) receive FFSB notification via IIE | IIE | IIE issues the FFSB letter (and IIE’s Outbound Advisors are introduced to finalists to begin collecting documents). After this date, Commissions/Posts may contact finalists. |  | 2025-03-01 | 2025-04-15 |  |  | March | April
U.S. Student | 2025-26 Selectees submit Medical Forms no later than 3 months prior to grant start. Commissions/Posts have access to medical clearance status. | Commission/Post | 2025-26 Participant medical statuses are available via the IIE Partner Portal. |  | 2025-03-15 | 2026-02-15 | January | February | March | April | May | June | July | August | September | October | November | December
U.S. Student | Instructions to 2025-26 Selectees regarding next steps. Fulbright Program Terms and Conditions available | Grantee | Pending method of communication: U.S. Fulbright Online - Finalist Resources or via Participant Portal |  | 2025-03-01 | 2025-04-15 |  |  | March | April
U.S. Student | Grant administration guidance for non-Commission countries provided to participants within 6 weeks of grant start at latest | Grantee | Advising Emails that include guidance on next steps and document collection. For reference, sample PDO PowerPoint presentations by region: · U.S. Fulbright Online - Africa PDO. · U.S. Fulbright Online - East Asia & the Pacific PDO. · U.S. Fulbright Online - Europe & Eurasia PDO. · U.S. Fulbright Online - Middle East & North Africa PDO. · U.S. Fulbright Online - South & Central Asia PDO. · U.S. Fulbright Online - Western Hem PDO |  | 2025-04-15 | 2026-01-15 | January |  |  | April | May | June | July | August | September | October | November | December
U.S. Student | Grant required documents collected through Participant Portal no later than 3 months prior to grant start. | Grantee | Commissions/Posts will have access to required documents via the IIE Partner Portal. |  | 2025-04-15 | 2026-01-15 | January |  |  | April | May | June | July | August | September | October | November | December
U.S. Student | Enroll 2025-26 Post participants in ASPE | IIE Action for Non-Commission Participants / Commission Action for Commission Participants | IIE enrolls participants in Post countries. Commissions enroll their participants. |  | 2025-06-15 | 2025-03-31
U.S. Student | Pre-Departure Orientations (Varies by World Region) | Grantee | Virtual PDO website for all countries: (password: mu2alxchange) |  | 2025-06-15 | 2025-07-31 | [5 empty] | June | July
U.S. Student | 2024-25 Participants arrive in host country | Grantee | Resources for current participants: U.S. Fulbright Online - Current Fulbrighters |  | 2024-07-01 | 2025-03-31 | January | February | March |  |  |  | July | August | September | October | November | December
U.S. Student | Participants reminded of Information on ASPE Assist 24/7 hotline in Sept./Jan. One month prior to grant start | Grantee | U.S. Fulbright Online - ASPE |  | 2024-09-01 | 2025-01-15 | January | [7 empty] | September | October | November | December
U.S. Student | Fulbright Commissions/Posts provide information to IIE for National Screening Committees (NSC) | Commission/Post | Survey issued by IIE |  | 2024-09-02 | 2024-10-01 | [8 empty] | September | October
U.S. Student | 2025-26 Application Cycle Deadline | IIE |  |  | 2024-10-08 | 2024-10-08 | [9 empty] | October
U.S. Student | IIE conducts Technical Review of 2025-26 applications | IIE | Fulbright Competition and Selection Timeline |  | 2024-10-15 | 2024-11-22 | [9 empty] | October | November
U.S. Student | National Screening Committee (NSC) Meetings Convene Early November to mid-December | IIE | U.S. Fulbright Online - NSC Member Resources. Guidelines for NSC Application Review and Rating |  | 2024-11-11 | 2024-12-16 | [10 empty] | November | December
U.S. Student | Mid-Terms Reports for 2024-25 Participants Available | IIE Action for Non-Commission Participants / Commission Action for Commission Participants | Fulbright Survey Report in IIE Partner Portal |  | 2024-11-15 | 2025-08-15 | January | February | March | April | May | June | July | August |  |  | November | December
U.S. Student | Participant Final Reports for 2024-25 Participants Due | IIE Action for Non-Commission Participants / Commission Action for Commission Participants | Fulbright Survey Report in IIE Partner Portal |  | 2025-02-01 | 2025-11-15 |  | February | March | April | May | June | July | August | September | October | November
U.S. Student | Non-Competitive Eligibility (NCE) forms mailed to Grantees six months into grant | IIE | Non-Competitive Eligibility (NCE) FAQs |  | 2024-12-01 | 2025-07-01 | January | February | March | April | May | June | July |  |  |  |  | December
U.S. Student | Certificates of Completion mailed to Alumni of 2024-25 participants one month after successful completion | Commission/Post | Commissions will verify grant completion. |  | 2025-06-01 | 2025-12-15 | [5 empty] | June | July | August | September | October | November | December
Visiting Scholar | 2025-26 Visiting Scholar Competitions close, Commission/Post receive applications and make selections in Slate | Commission/Post | Commission/Post Slate Portal |  | 2024-08-01 | 2024-12-31 | [7 empty] | August | September | October | November | December
Visiting Scholar | Commission/Post transmits recommended candidates to ECA and IIE via Slate by January 15, 2025 (Posts) and February 1, 2025 (Commissions) | Commission/Post | Commission/Post Slate Portal | Deadline for Posts: January 15, 2025 Deadline for Commissions: February 1, 2025 | 2024-10-01 | 2025-02-01 |  | February | [7 empty] | October | November | December
Visiting Scholar | Upon panel submission by the field to ECA, IIE commences technical review of applications, including plagiarism review, and migrates data into IIE’s Partner Portal where Commissions and Posts can view participant records live. | IIE | Plagiarism Review Process (Historical from Rollout) | Panels will be completely reviewed within one month of receipt. | 2024-10-01 | 2025-03-15 | January | February | March | [6 empty] | October | November | December
Visiting Scholar | Post/IIE administered countries: IIE/ECA prepare 2025-2026 budgets. ECA confirms selected participants with Post after technical review and budgets completed and FFSB approval received. Commission-paid countries: ECA confirms selected participants with Commission after technical review completed and FFSB approval received. Any participants with potential J-visa restrictions or candidates requiring a No-patient contact letter (Medical Sciences memo) are flagged. | IIE | Scholar Website - Medical Sciences/No Patient Contact Letter |  | 2025-02-01 | 2025-05-31 |  | February | March | April | May
Visiting Scholar | IIE launches Visiting Scholar competition for 2026-2027 cycle (FY26). | IIE | Fulbright Application (Slate) -FY26 Visiting Scholar Application will open by January 1, 2025 | Announcement to open FY25 Visiting Scholar competitions shared with the field in January 2024 Fulbright Bulletin | 2024-12-01 | 2025-01-01 | January | [10 empty] | December
Visiting Scholar | IIE Communicates Tax Responsibilities to participants about their tax obligations for tax year 2024 and provides tax services to those with IIE-paid income/enrichment program benefits. | IIE | Visiting Scholar Guide: Reporting Your Taxes | The cost of Sprintax Services will be covered for all Fulbright scholars who received taxable Fulbright program benefits. | 2025-01-01 | 2024-03-15
Visiting Scholar | Participants who received IIE-paid income (whether stipends or enrichment/OLF benefits) independently supply the appropriate paperwork to Sprintax and file their own returns independently. Scholars who did not receive IIE income will receive instructions to guide them on minor tax-related paperwork (typically form 8843). | Grantee | Visiting Scholar Guide: Reporting Your Taxes | The cost of Sprintax Services will be covered for all Fulbright scholars who received taxable Fulbright program benefits. | 2025-03-01 | 2025-04-15 |  |  | March | April
Visiting Scholar | Commissions/Posts launch their FY26 competitions in Slate by country. | Commission/Post | Commission/Post Slate Portal | Review Resources Tab for Trainings/Instructions | 2025-01-01 | 2025-10-01 | January | February | March | April | May | June | July | August | September | October
Visiting Scholar | Commissions/Posts provide completed medical forms to IIE | Commission/Post | Scholar-Website/Medical Form | Selectees must have their medical examination no more than six months prior to their start date. | 2025-02-01 | 2025-12-01 |  | February | March | April | May | June | July | August | September | October | November | December
Visiting Scholar | Commissions/Posts provide supporting materials (in conversation with nominee), such as all documents, J1 and J2 verifications (including financial support information and medical sciences forms), as needed through the IIE Partner Portal | Commission/Post | DS-2019 Checklist | Heaviest in Spring/Summer | 2025-02-01 | 2025-12-31 |  | February | March | April | May | June | July | August | September | October | November | December
Visiting Scholar | IIE issues Affiliation (Institutional Reply Form/IRF) and issues Participant Activity Review through the IIE Partner Portal for scholar and Commission/Post review. IIE Placement Services Upon Request | IIE | IIE Placement Services Form | Heaviest in Spring/Summer | 2025-02-01 | 2025-12-31 |  | February | March | April | May | June | July | August | September | October | November | December
Visiting Scholar | Once Commissions/Posts share IRF with participant and confirms program dates, Commissions/Posts submit confirmations through the IIE Partner Portal | Commission/Post | IIE Partner Portal | Heaviest in Spring/Summer | 2025-03-01 | 2025-12-31 |  |  | March | April | May | June | July | August | September | October | November | December
Visiting Scholar | IIE issues Terms and Conditions of Award and transfers to Commissions and Posts through the IIE Partner Portal. | IIE | IIE Partner Portal | Heaviest in Spring/Summer | 2025-02-01 | 2025-12-31 |  | February | March | April | May | June | July | August | September | October | November | December
Visiting Scholar | Posts work with selectee to review and sign Grant documents, Terms and Conditions of Award; Commissions issue grant documents; Commissions and Posts submit signed grant documents through the IIE Partner Portal. | Commission/Post | IIE Partner Portal | Heaviest in Spring/Summer | 2025-02-01 | 2025-12-31 |  | February | March | April | May | June | July | August | September | October | November | December
Visiting Scholar | IIE issues Forms DS-2019 upon receipt of all supporting documents and signed grant documents/terms and conditions | IIE | IIE Partner Portal | Heaviest in Spring/Summer | 2025-04-01 | 2025-12-31 |  |  |  | April | May | June | July | August | September | October | November | December
Visiting Scholar | Commissions and Posts can see predicted issuing dates and N numbers in the IIE Partner Portal. | Commission/Post | IIE Partner Portal | Heaviest in Spring/Summer | 2025-04-01 | 2025-12-31 |  |  |  | April | May | June | July | August | September | October | November | December
Visiting Scholar | Pre-Departure Orientations (Varies by country) | Commission/Post | Scholar Website (PDO Powerpoint decks, Fulbright Scholar Guide) | Password=Resources | 2025-03-01 | 2025-07-31 |  |  | March | April | May | June | July
Visiting Scholar | IIE welcomes scholars to the United States and shares digital grant packet. Enroll participants (not dependents) in ASPE. Access to Self-Service Portal. IIE administers baseline survey to participants before arrival in country. Most FY24 participants arrive for full academic year grants in the Fall of 2024 and grants should conform to the U.S. academic calendar to the extent possible. The last possible start date for the FY24 cohort is May 31, 2025. | IIE | Self-Service Portal. Scholar Website - Visiting Scholar Digital Grant Packet (password: Resources). | Ongoing throughout the year | 2025-07-01 | 2025-05-31
Visiting Scholar | 2025-2026 Participants arrive in United States. Participants notify IIE of their arrival via Self-Service Portal. Participants should arrive for full academic year grants in the Fall of 2025 and conform to the U.S. academic calendar to the extent possible. The last possible start date for the FY25 cohort is May 31, 2026 | Grantee | Self-Service Portal | Rolling according to planned start dates | 2025-07-01 | 2026-05-31 | January | February | March | April | May |  | July | August | September | October | November | December
Visiting Scholar | IIE will inform Commission/Post of any grant issues or changes in grant | IIE |  | Ongoing throughout the year | 2024-10-01 | 2025-09-30 | January | February | March | April | May | June | July | August | September | October | November | December
Visiting Scholar | IIE provies in-country advising services and touch points to Visiting Scholars | IIE | Scholar Website - Visiting Scholar Program Advisors | Ongoing throughout the year | 2024-10-01 | 2025-09-30 | January | February | March | April | May | June | July | August | September | October | November | December
Visiting Scholar | IIE administers mid-term monitoring survey to participants who are on grant longer than six months | IIE |  | Ongoing throughout the year | 2024-10-01 | 2025-09-30 | January | February | March | April | May | June | July | August | September | October | November | December
Visiting Scholar | Participants inform IIE of any changes in their grant, including but limited to: o Changes in personal status o Program progress or challenges o Health problems (including pregnancies) and legal issues o International travel o Employment and honoraria o Extensions of stay o Transfers of sponsorship o Departure travel | Grantee |  | Ongoing throughout the year | 2024-10-01 | 2025-09-30 | January | February | March | April | May | June | July | August | September | October | November | December
Visiting Scholar | IIE administers final survey to participants upon completion of grant and shares responses with Commissions and Posts as individual participant reports through the IIE Partner Portal. | IIE | IIE Partner Portal | Ongoing throughout the year | 2024-10-01 | 2025-09-30 | January | February | March | April | May | June | July | August | September | October | November | December
Visiting Scholar | IIE provides electronic certificates through the self-service portal upon completion of final survey. | IIE | Self-Service Portal | Ongoing throughout the year | 2024-10-01 | 2025-09-30 | January | February | March | April | May | June | July | August | September | October | November | December
This shape represents a table slicer. Table slicers are not supported in this version of Excel. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2007 or earlier, the slicer can't be used.
This shape represents a table slicer. Table slicers are not supported in this version of Excel. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2007 or earlier, the slicer can't be used.
This shape represents a table slicer. Table slicers are not supported in this version of Excel. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2007 or earlier, the slicer can't be used.
This shape represents a table slicer. Table slicers are not supported in this version of Excel. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2007 or earlier, the slicer can't be used.
This shape represents a table slicer. Table slicers are not supported in this version of Excel. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2007 or earlier, the slicer can't be used.
This shape represents a table slicer. Table slicers are not supported in this version of Excel. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2007 or earlier, the slicer can't be used.
This shape represents a table slicer. Table slicers are not supported in this version of Excel. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2007 or earlier, the slicer can't be used.
This shape represents a table slicer. Table slicers are not supported in this version of Excel. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2007 or earlier, the slicer can't be used.
This shape represents a table slicer. Table slicers are not supported in this version of Excel. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2007 or earlier, the slicer can't be used.
This shape represents a table slicer. Table slicers are not supported in this version of Excel. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2007 or earlier, the slicer can't be used.
This shape represents a table slicer. Table slicers are not supported in this version of Excel. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2007 or earlier, the slicer can't be used.
This shape represents a table slicer. Table slicers are not supported in this version of Excel. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2007 or earlier, the slicer can't be used.